## Title
#VALUE!
Somes Island Area School
5YA starting 2024
Example - 10YPP Condition Assessment Reports
2024 to 2033
Prepared by
Joanne Moyer
26/09/2016
Powered by WebFM - MPlan
Updated 5YA Year
2024-07-22

## 10YPP Strategic Impacts
Facility Name | Somes Island Area School
Count of Start Year | Start Year
Impact | 24/25 | 26/27 | Grand Total
2024 Boiler/Heating Infrastructure Report attached. Maintenance works included in CA. | 1 |  | 1
2024 Drain laying Infrastructure Report attached. Maintenance works included in CA. | 1 |  | 1
2024 Electrical Infrastructure Report attached. Maintenance works included in CA. | 1 |  | 1
2024 Plumbing Infrastructure Report attached. Maintenance works included in CA. | 1 |  | 1
2024 Roofing Infrastructure Report attached. Maintenance works included in CA. | 1 |  | 1
Block 1 (Junior Admin) identified on National Weather-tighness survey with cladding repairs of $180,000 and isolated repairs of $20,000. Blocks confirmed on MoE low priority list. Update Oct 2023: Works and costs removed from CA. | 1 |  | 1
Block 5 has been demolished but still showing in Helios. Asset Update form attached and submitted to MoE 1/1/24. Given Maintenance Standard D. | 1 |  | 1
Block 7 on site but not showing in Helios. CA items have been loaded against site. Asset Update form attached and submitted to Property Advisor 01/02/2024. | 1 |  | 1
School has programmed maintenance painting contract in place for external painting (all blocks) which expires 2027. Annual contract cost of $20K has been included against site (PRO). Copy of contract attached. | 1 |  | 1
Structural Assessment undertaken for Block 2 where initial EQP score rated greater than 75. Report outlining deficiencies and possible solutions attached. Update Oct 2023: Confirmed with NZSPA that no further strengthening work required on block. Wo | 1 |  | 1
Block 3 identified on National weather-tightness survey for cladding replacement $200k and roof replacement $100k. Confirmed on MoE WTP high priority list. Updated Aug 2015 - work will now take place 2025 and budget $400k. Work item updated in CA. |  | 1 | 1
Grand Total | 10 | 1 | 11

## 10YPP - Capital Maintenance
Facility Name | Somes Island Area School
Sum of Cost | Column Labels
Row Labels | 2025/26 | 2026/27 | 2027/28 | 2029/30 | Grand Total
Block 3 |  | 400000 | 35000 | 20000 | 455000
Capital Maintenance |  |  | 35000 | 20000 | 55000
5 |  |  | 35000 | 20000 | 55000
Replace carpet (80%) and vinyl (20%) |  |  | 35000 |  | 35000
Replacing x4 heat pumps |  |  |  | 20000 | 20000
Weather Tightness |  | 400000 |  |  | 400000
2 |  | 400000 |  |  | 400000
Weather-tightness works - cladding replacement and roof replacement. |  | 400000 |  |  | 400000
Block 4 | 35000 |  |  |  | 35000
Capital Maintenance | 35000 |  |  |  | 35000
3 | 30000 |  |  |  | 30000
Replace roof, as per Infrastructure Report. | 30000 |  |  |  | 30000
5 | 5000 |  |  |  | 5000
Replace ceiling mounted sockets and plugs above Stage | 5000 |  |  |  | 5000
New 3 Class Block SPG | 52000 |  |  |  | 52000
Capital Maintenance | 52000 |  |  |  | 52000
5 | 52000 |  |  |  | 52000
Replace heat damaged light fittings | 52000 |  |  |  | 52000
Somes Island Area SCHOOL |  |  | 10000 |  | 10000
Capital Maintenance |  |  | 10000 |  | 10000
5 |  |  | 10000 |  | 10000
Block 7 - replace 2 heat pumps |  |  | 10000 |  | 10000
UPPER LOWER BLOCK | 40000 |  |  |  | 40000
Capital Maintenance | 40000 |  |  |  | 40000
5 | 40000 |  |  |  | 40000
Replace toilet pans, sinks and partitions | 40000 |  |  |  | 40000
Grand Total | 127000 | 400000 | 45000 | 20000 | 592000

## 10YPP - Cyclical Works
Facility Name | Somes Island Area School
Sum of Cost | Column Labels
Row Labels | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2033/34 | Grand Total
Block 3 | Column Labels 2028/29: 12000 | 12000
Cyclical Maintenance | Column Labels 2028/29: 12000 | 12000
5 | Column Labels 2028/29: 12000 | 12000
Repaint interior including ceilings, doors and windows. | Column Labels 2028/29: 12000 | 12000
Block 4 | Column Labels 2028/29: 42000 | 42000
Cyclical Maintenance | Column Labels 2028/29: 42000 | 42000
5 | Column Labels 2028/29: 42000 | 42000
Internal repaint including fixed storage units and ceilings | Column Labels 2028/29: 30000 | 30000
Repaint interiors including windows and doors | Column Labels 2028/29: 12000 | 12000
Somes Island Area SCHOOL | 60000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 200000
Programme Maintenance | 60000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 200000
3 | 60000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 200000
Repaint exterior (programme maintenance contract) | 60000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 200000
Grand Total | 60000 | 20000 | 20000 | 74000 | 20000 | 20000 | 20000 | 20000 | 254000

## Asset & Sub Asset
Asset Code | Asset Name | Sub Asset Code | Sub Asset Name
MOE | Ministry Of Education | 01 | Advanced Training
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What would these become?

## Facility & Building
Asset Code | Asset Name | Sub Asst Code | Sub Asset Name | Facility Code | Facility Name | Building Code | Building Name | Standard Code | Standard
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 1 | JUNIOR ADMIN | B | General
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 2 | UPPER LOWER BLOCK | B | General
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | General
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 3 | Block 3 | B | General
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 4 | Block 4 | B | General
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 5 | Block 5 | D | Mothball
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 6 | New 3 Class Block SPG | B | General

## Strategic Impact
Asset Code | Asset Name | Sub Asset Code | Sub Asset Name | Facility Code | Facility Name | Building Code | Building Name | Standard | Impact | Start Year | End Year | Created By | Created On | Updated By | Updated On
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 2 | UPPER LOWER BLOCK | B | Structural Assessment undertaken for Block 2 where initial EQP score rated greater than 75. Report outlining deficiencies and possible solutions attached. Update Oct 2015: Confirmed with NZSPA that no further strengthening work required on block. Work item therefore removed from CA. | 25/26 | 25/26 | Charlie Wu | 2024-10-13 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | School has programmed maintenance painting contract in place for external painting (all blocks) which expires 2027. Annual contract cost of $20K has been included against site (PRO). Copy of contract attached. | 25/26 | 30/31 | Charlie Wu | 2024-10-13 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | Block 7 on site but not showing in Helios. CA items have been loaded against site. Asset Update form attached and submitted to Property Advisor 01/02/2014. | 25/26 | 25/26 | Charlie Wu | 2024-10-13 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 1 | JUNIOR ADMIN | B | Block 1 (Junior Admin) identified on National Weather-tighness survey with cladding repairs of $180,000 and isolated repairs of $20,000. Blocks confirmed on NZSPA low priority list. Update Oct 2024: Works and costs removed from CA. | 25/26 | 25/26 | Charlie Wu | 2024-10-13 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | 2024 Roofing Infrastructure Report attached. Maintenance works included in CA. | 25/26 | 30/31 | Joanne Moyer | 2024-11-10 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | 2024 Electrical Infrastructure Report attached. Maintenance works included in CA. | 25/26 | 30/31 | Joanne Moyer | 2024-11-10 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | 2024 Boiler/Heating Infrastructure Report attached. Maintenance works included in CA. | 25/26 | 30/31 | Joanne Moyer | 2024-11-10 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | 2024 Plumbing Infrastructure Report attached. Maintenance works included in CA. | 25/26 | 30/31 | Joanne Moyer | 2024-11-10 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL | B | 2024 Drain laying Infrastructure Report attached. Maintenance works included in CA. | 25/26 | 30/31 | Joanne Moyer | 2024-11-10 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 5 | Block 5 | D | Block 5 has been demolished but still showing in Helios. Asset Update form attached and submitted to NZSPA 1/1/24. Given Maintenance Standard D. | 25/26 | 26/27 | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2025-09-26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 6 | New 3 Class Block SPG | B | Block 3 identified on National weather-tightness survey for cladding replacement $200k and roof replacement $100k. Confirmed on NZSPA WTP high priority list. Updated Aug 2023 - work will now take place 2025 and budget $400k. Work item updated in CA. Other works on this block have been scheduled to occur after this. | 27/28 | 28/29 | Joanne Moyer | 2025-10-06 | Joanne Moyer | 2025-09-26

## Condition Survey Report
Asset Class Code | Asset Class | Sub Asset Class Code | Sub Asset | Facility Code | Facility Name | Building Code | Building Name | Level Code | Level Name | Element Code | Element | Sub Element Code | Sub Element | Job Type Code | Job Type | Standard Code | Standard | Location Description | Description | Trade Code | Trade | Unit | Quantity | Cost | Frequency | Start Year | Priority Code | Priority | Status | Created By | Created On | Updated By | Updated On | Condition Survey Key | Base Start Year
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 2 | UPPER LOWER BLOCK |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | North end toilet block | Replace toilet pans, sinks and partitions and repaint walls | PL | Plumber / Drain layer |  | 0 | 40000 | 0 | 2025/26 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 9995fc945164443f229c5bab9e7e761a | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2025/26 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 4 | Block 4 |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | Stage area | Replace ceiling mounted sockets and plugs above Stage | EL | Electrician |  | 0 | 5000 | 0 | 2025/26 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 1df3b9e609ca9b6d5df7badeacfc39dc | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 6 | New 3 Class Block SPG |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | Whole block | Replace heat damaged light fittings | EL | Electrician |  | 0 | 52000 | 0 | 2025/26 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 5ba1e53b280ab758159f7e4d7779dc94 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2025/26 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 4 | Block 4 |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | Whole block | Replace roof, as per Infrastructure Report. | RO | Roofer |  | 0 | 30000 | 25 | 2025/26 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 247a1dc1701ad957208872d875387aca | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2026/27 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 3 | Block 3 |  | All | EL | Elements | BF | Building Fabric | WTP | Weather Tightness | B | General | Whole block | Weather-tightness works - cladding replacement and roof replacement. | OT | Other |  | 0 | 400000 | 0 | 2026/27 | 2 | High Operational Risk | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | cd59033109bdfbe255feaf613376ff11 | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | Block 7 | Block 7 - replace 2 heat pumps | HV | Heating, Ventilation and AC |  | 2 | 10000 | 7 | 2027/28 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 26a759bdf3428e8370926e9ac8622e0b | 2027/28
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2027/28 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 3 | Block 3 |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | Rooms 3, and 5, art resource room and all corridors | Replace carpet (80%) and vinyl (20%) | FC | Floor Coverings |  | 0 | 35000 | 0 | 2027/28 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | e087928aeec0cfe360876567a931598e | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2028/29 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2024/25
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 3 | Block 3 |  | All | EL | Elements | BF | Building Fabric | CYC | Cyclical Maintenance | B | General | All classrooms and corridors (excluding resource rooms) | Repaint interior including ceilings, doors and windows. | PI | Painter Internal |  | 0 | 12000 | 10 | 2028/29 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 7e904dd98eb0030ce6c9018d35a88c91 | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 4 | Block 4 |  | All | EL | Elements | BF | Building Fabric | CYC | Cyclical Maintenance | B | General | Whole block | Repaint interiors including windows and doors | PI | Painter Internal |  | 0 | 12000 | 0 | 2028/29 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 2ae17d960e808234317459fa3d77704e | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 4 | Block 4 |  | All | EL | Elements | BF | Building Fabric | CYC | Cyclical Maintenance | B | General | Whole block | Internal repaint including fixed storage units and ceilings | PI | Painter Internal |  | 0 | 30000 | 0 | 2028/29 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 241377d80ed579ba5faae457ddf69408 | 2028/29
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2029/30 | 3 | Asset Preservation | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 3 | Block 3 |  | All | EL | Elements | BF | Building Fabric | CAP | Capital Maintenance | B | General | All classrooms | Replacing x4 heat pumps | HV | Heating, Ventilation and AC |  | 0 | 20000 | 0 | 2029/30 | 5 | Lifecycle replacement | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | fa09e4dec8f61dc9c859a265f4ce7f95 | 2030/31
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2030/31 | 3 | Asset Preservation | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2025/26 | 3 | Asset Preservation | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2031/32 | 3 | Asset Preservation | Planned | Joanne Moyer | 2024-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26
MOE | Ministry Of Education | 01 | Advanced Training | A03 | Somes Island Area School | 233 | Somes Island Area SCHOOL |  | All | EL | Elements | BF | Building Fabric | PRO | Programme Maintenance | B | General | Exterior all buildings | Repaint exterior (programme maintenance contract) | PE | Painter External |  | 0 | 20000 | 1 | 2033/34 | 3 | Asset Preservation | Planned | Joanne Moyer | 2025-01-07 | Joanne Moyer | 2024-01-07 | 185e9285edff759bfc6402ef8b97b710 | 2025/26

## Element & Sub Element
Element Code | Element Name | Sub Element Code | Sub Element Name
EL | Elements | BF | Building Fabric
EL | Elements | PS | Plumbing Services
EL | Elements | HV | Heating, Ventilation and Air Conditioning
EL | Elements | IN | Infrastructure
EL | Elements | ES | Electrical Systems
EL | Elements | FS | Fire Protection Systems
EL | Elements | VT | Vertical Transportation